## Agile Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Team 11 - ERP Solution | Kevin L. | 2021-01-13 | 2021-04-20 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  |  | 2021-01-13 | 2021-02-03 | 21 | Complete
| Account Creation | User Type | Sunny D. & Kim H. | 1 | 2021-01-19 | 2021-01-24 | 6 | Complete | Current focus on a generic user with focus on administrative functionality.
| Login | User Type | Sunny D. & Kim H. | 1 | 2021-01-28 | 2021-01-28 | 1 | Complete | Allow generic login of any registered user. Role-based segregation will be done at a later Sprint.
| Sprint 2 |  |  |  | 2021-02-04 | 2021-02-24 | 21 | Not Started
| Product Creation | Bike Type | Kevin L. | 2 | 2021-02-04 | 2021-02-24 | 21 | Not Started
| Material Creation, Tracking, and Editing | Bike Type | Omar S. | 8 | 2021-02-04 | 2021-02-24 | 21 | Not Started
| Inventory Tracking | Bike Type | Sunny D. | 5 | 2021-02-04 | 2021-02-24 | 21 | Not Started

## Notes
Story Points | Follows the Fibonacci Sequence, up to 13
1 | Very small amount of work
2
3
5
8
13 | Largest expected amount of work
This was chosen based because of the large difference in points between a small and large tasks
It was also chosen in reference to the following website: https://www.lucidchart.com/blog/fibonacci-scale-for-agile-estimation

## -Disclaimer-
Please update this as per your ERP system name and policies you want to adopt